

Movement Makers Training and Outreach Plan

 **Vision of Success (by 2021):**

|  |  |  |
| --- | --- | --- |
| * See action across the community grow in the areas identified in learning conversations
* See measurable change in community in the issues identified in learning conversations
* Enjoy, celebrate and know each other and neighbors.
 | * People feel their assets are matched to their day to day life actions
* Supporting one another isn’t rare - Community felts taken care of by each other, associations, and communities.
 | * Anchor Institution Policy change and Decision Making occurs due to influence from community
* Large scale changes are seen as everyday
* Associations and institutions are highly connected to the residents and neighborhoods they are in
 |

 **Action Team Purpose**: To expand East5ide Unified Unido understanding of and use of Asset Based Community Development (ABCD) Principles and approaches; to promote community connectivity through outreach and engagement; to support community leadership development

 **Action Team Deliverables:**

|  |  |
| --- | --- |
| * Develop Team of Community Connector(s)
 | * Recruit participation from: Whittier, Clayton, Cole, Five Points, and Skyland
 |
| * Create an ABCD resource inventory/guide
 | * Host 2-3 East5ide generated activities
 |
|  | * Resources and assets
 |

 Measures of Progress: to be quantified

* Grow Circles of Connection through ABCD Principles and Activities.
* Build a shared pool of understanding and knowledge of Asset Based Community Development - Regular connection to other action teams to infuse ABCD.
* Harness the advantage of acting collectively; do something together.
* Maximize the momentum and power that comes from learning and exploring together.
* Leverage the assets all anchor institution partners bring and build community awareness of these assets.
* Living EU values, principles.

|  |  |  |  |
| --- | --- | --- | --- |
| Action*What Will Be Done?* | Who*Who Will Do It?* | Timeline*By When? (Day/Month)* | Resources1. *Resources Available*
2. *Resources Needed (ex: money, people, etc.)*
 |
| Train a team in ABCD | TashBenzelRobertaKellieEmily | October 2018CheckmarkTBD, 2019TBD, 2020 | A. Tamarack Training, others?B. Funds through HDGP available |
| Host an ABCD Debrief with EU | TashBenzelRobertaKellieEmily | CheckmarkNovember 2018TBD, 2019TBD, 2020 | A. Training space at Ford WarrenB. Training resources |
| Form ABCD/Community Action Team* Roberta, Benzel, Vonda, Jada, Bintou, Lois, Sandy, Jason, Tash
 | MM Team | CheckmarkFebruary 2019  | 1. Interested people!
2. We need people to co-lead this (not Emily) – get times to meet set, work together on planning actions
 |
| Convene Regular MM Action Team Meetings | MM Team LeadEmilyConnector | CheckmarkMarch 2019April 24 2019  | 1. Tramway Space, people
2. Need someone to lead this
 |
| Identify ongoing ABCD Technical Assistance Supports and Needs | MM Action Team | June 2019ongoing | 1. Local ABCD experts – Ruben Medina, Beckah Tuerlow, Mike Green
2. Training books
3. Own knowledge
4. EU Guiding Principles
5. What are we missing? How to use?
 |
| Scope out role for Community Connector(s) | EU Coordinator (Emily)MM Action Team | CheckmarkFebruary-March 2019  | 1. Emily has a draft for team to look at
 |
| Recruit Community Connector(s) | EU Coordinator (Emily)MM Action Team | CheckmarkMarch/April 2019  | 1. Need help from this group to review, share, and then interview
 |
| Onboard community connectors | EU Coordinator (Emily)MM Action Team | May 2019 | 1. Emily can start
2. Need team to do meetings with, think of who they need to know
 |
| Compile an inventory of ABCD resources, strategies and best practices (e.g. 2-3 page document with links for more information) | MM Action Team | February 2019 CheckmarkUpdate as needed | A. Existing resources and information via local resources, training resources, additional resources.B. Review at.. |
| Understand how to regularly use ABCD materials, and infuse into EU work | MM Action Team | July 2019 |  |
| Co-Design Community event with Anchor Institution Action Team | MM Action TeamCommunity Coordinator | May 2019 | 1. Rough Idea in place – Chuck Ault
2. Who can help? Need a lead
 |
| Community Coordinator(s) develop outreach plan for the 5 communities |  | July – November 2019 | 1. Connect with Council Members
2. Visit Neighborhoods
3. Determine tools needed for communication – flyer, text, etc
4. Identify outreach plan for engaging legacy and new residents
 |
| Support Learning Conversations to Occur (trainings, check ins, debriefs) | Community Coordinator | CheckmarkQ2 2019 Quarterly | 1. Benzel has ground work laid!
2. Develop cadence
 |
| Support activities that connect neighbors (eg gift parties from eu, block parties, other existing events) 2-3 eu generated, 3-6 existing in the neighborhood | Community CoordinatorMM Action Team | CheckmarkQ2 2019 Quarterly | 1. Host quarterly gift parties
2.
 |
| Identify training opportunities for EU network (hard and soft skills) |  | OngoingJuly 2019 | 1. Monitor opportunities
2. Plan events
3. Determine cadence of eu events
 |
| Identify strategy to connect to existing neighborhood events and activities | Community CoordinatorMM Action Team | August 2019 | 1.
2.
 |
| Ensure multiple ways for East Denver to know about EU and neighborhood activities (eg website, newsletter, social media, etc) | Community CoordinatorMM Action Team | July 2019 | 1. Investigate what is going on now
2. Compile list of communication channels
3. Consider 1 80205 newsleter?
 |
| Connect community members to existing neighborhood policy related issues, current events | Community CoordinatorMM Action Team | July 2019 | 1. Document opportunities, associations, orgs doing this work
2. Ask what EU is interested in
3. Share opportunities
 |
| Develop regular connects to Anchor Institution action team (to inform AI policy change), Eval and Learning action team | Community CoordinatorMM Action TeamEmily | OngoingRoutine by May 2019 | 1.
2.
 |
| Identify plan for mapping the history and assets of 80205 |  |  |  |

Who do you need to recruit to help accomplish the goal?

* Someone from each of the 5 neighborhoods
* Legacy residents
* People who love outreach

|  |
| --- |
| Who is involved |
| First Name | Last Name | Cell | Email |
| Roberta  | Molock |  |  |
| Benzel | Jimmerson |  |  |
| Vonda | Molock |  |  |
| Bintou | Diallou |  |  |
| Jason | Vitello |  |  |
| Sandy | Douglas |  |  |
| Tash | Mitchell |  |  |
| Emily | Holcomb |  |  |
| Lois | Doll |  |  |
| Gerald | Hamel |  |  |
| Jenee | Donnelson |  |  |